Revenue Budget

Annual Procurement Plan (2018-2019)

| Ministry/ Division |  | Ministry of Road Transport & Bridges/Bridges Division |  |
| --- | --- | --- | --- |
| Agency |  | Bangladesh Bridge Authority |  |  |
| Procuring Entity Name & Code |  | Bangladesh Bridge Authority | 7105 |  |  |
| Project/ Program Name & Code |  | Technical Wing |  |  |  |

| Package No. | Description of Procurement package as per DPP WORKS | Unit | Quantity | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost (in Lac Taka) | Time code for process | Advertise prequel (if applicable) | Tender opening | Invite/ Advertise Tender | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract signing | Time for completion of contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| WD01 | Construction of Truck lane (Extension) | - | LS | OTM | BBA | GOB/BBA Own Fund | 2400.00 | Planned Dates |  |  | July 18 | Sept 18 | Oct 18 | Oct 18 | Oct 18 | 120 days | 12 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| WD02 | Answer Accommodation housing facilities | - | LS | OTM | BBA | GOB/BBA Own Fund | 112.00 | Planned Dates |  |  | April 18 | July 18 | Aug 18 | Aug 18 | Aug 18 | 120 days | 12 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| GD01 | Supply Installation Weigh Scale at BBA | - | LS | OTM | BBA | GOB/BBA Own Fund | 400.00 | Planned Dates |  |  | March 18 | July 18 | Aug 18 | Aug 18 | Aug 18 | 150 days | 12 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| GD02 | Supply Installation Sodium Light at BBA | - | LS | OTM | BBA | GOB/BBA Own Fund | 80.00 | Planned Dates |  |  | May 18 | July 18 | Aug 18 | Aug 18 | Aug 18 | 120 days | 6 month |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| SD01 | Consultancy Service Hydrological Morphological of Jamuna river vanity of Bangabandhu Bridge. | - | LS | RFP | BBA | GOB/BBA Own Fund | 500.00 | Planned Dates |  | February 18 | Jan 18 | Aug 18 | Sept 18 | Oct 18 | Oct 18 | 240 days | 60 month |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |

Annual Procurement Plan (2018-2019)

| Ministry/ Division |  | Ministry of Road Transport & Bridges/Bridges Division |  |
| --- | --- | --- | --- |
| Agency |  | Bangladesh Bridge Authority |  |  |
| Procuring Entity Name & Code |  | Bangladesh Bridge Authority | 7105 |  |  |
| Project/ Program Name & Code |  | Technical Wing (Mukterpur Bridge) |  |  |  |

| Package No. | Description of Procurement package as per DPP WORKS | Unit | Quantity | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost (in Lac Taka) | Time code for process | Advertise prequel (if applicable) | Tender opening | Invite/ Advertise Tender | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract signing | Time for completion of contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| WR 01 | Construction of Boundary Wall both side of the Mukterpur Bridge | No | 1 | OTM | BBA | GOB/BBA Own Fund | 350.00 | Planned Dates |  |  | September 18 | November 18 | December18 | January 18 | January 18 | 150 days | 9 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| WR 02 | Repair and Re- Construction of Mukterpur Approach Road | No | 1 | OTM | BBA | GOB/BBA Own Fund | 850.00 | Planned Dates |  |  | October 18 | November 18 | December18 | January 18 | January 18 | 120 days | 9 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| WR | Construction of Staff Accomodation for Ansar & Toll Operator | No | 1 | OTM | BBA | GOB/BBA Own Fund | 300.00 | Planned Dates |  |  | October 18 | November 18 | December18 | January 18 | January 18 | 120 days | 18 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| WR 03 | Construction of Toll Plaza Shed at Munshgangj side of Munkerpur Bridge | No | 1 | OTM | BBA | GOB/BBA Own Fund | 250.00 | Planned Dates |  |  | October 18 | November 18 | December18 | January 18 | January 18 | 120 days | 9 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| WR 04 | Construction of Toll Plaza Monitoring Building at Munshgangj side of Munkerpur Bridge | No | 1 | OTM | BBA | GOB/BBA Own Fund | 120.00 | Planned Dates |  |  | September 18 | November 18 | December18 | January 18 | January 18 | 150 days | 18 months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  |  |
| WR 05 | Construction of Boundary Wall around Office cum Rest House of the Mukterpur Bridge | No | 1 | OTM | BBA | GOB/BBA Own Fund | 40.00 | Planned Dates |  |  | October 18 | November 18 | December18 | January 18 | January 18 | 90 days | 6 months |
|  |  |  |  |  |  |  |  | Planned Dates |  |  |  |  |  |  |  |  |  |

Annual Procurement Plan (2018-2019)

| Ministry/ Division |  | Ministry of Road Transport & Bridges/Bridges Division |  |
| --- | --- | --- | --- |
| Agency |  | Bangladesh Bridge Authority |  |  |
| Procuring Entity Name & Code |  | Bangladesh Bridge Authority | 7105 |  |  |
| Project/ Program Name & Code |  | Administration Wing |  |  |  |

ICT Cell

| Package No. | Description of procurement package works | Unit | Procurement Method & Type | Contract Approving Authority | Source Of Funds | Estd. Cos in Lac Tk. | Time Code for process | Not Used in goods | Invite/ Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing Of Contract | Total time to Contract Signing | Time for Completion of Contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 1. | Computer Purchase | 15 | OTM / RFQ | BBA | GOB | 10 | - | - | Nov/18 | Dec/18 | Dec/18 | Dec/18 | Jan/18 | Feb/19 | 4 Months | 4 Months |
| 2. | Land Management System | 1 | OTM | BBA | GOB | 45 | - | - | Jun/18 | July/18 | Aug/18 | Oct/18 | Nov/18 | Dec/18 | 6 Months | 18 Months |
| 3. | Network/Hardware Maintenance | - | OTM | BBA | GOB | 10 | - | - | Nov/18 | Jan/19 | Feb/19 | Mar/19 | Mar/19 | Apr/19 | 4 months (After Approval of Estimate) | 6 months |
| 4. | Office equipment purchase | - | RFQ/DTM | BBA | GOB | 6 | - | - | - | - | Oct/18 | Oct/18 | Nov/18 | Dec/18 | 3 months | 5 Months |
| 5. | Extension of Existing Surveillance System of BBA Head Office | 1 | RFQ | BBA | GOB | 3 | - | - | Oct/18 | Nov/18 | Nov/18 | Nov/18 | Nov/18 | Nov/18 | 1 Months | 3 Months |
| 6. | Training Management System | 1 | RFQ | BBA | GOB | 2 | - | - | Feb/19 | Feb/19 | Feb/19 | Mar/19 | Mar/19 | Mar/19 | 4 Months | 3 Months |
| 7. | SMS Purchase | 60,000 | RFQ | BBA | GOB | 1 | - | - | Oct/18 | Oct/18 | Nov/18 | Nov/18 | Nov/18 | Nov/18 | 2 Months | 3 Months |
| 8. | Software Maintenance |  | RFQ | BBA | GOB | 4 | - | - | Nov/18 | Jan/19 | Feb/19 | Mar/19 | Mar/19 | Apr/19 | 4 months (After Approval of Estimate) | 6 months |
| 9. | Software Purchase | 3 | RFQ | BBA | GOB | 3 | - | - | Oct/18 | Oct/18 | Nov/18 | Nov/18 | Nov/18 | Nov/18 | 2 Months | 2 Months |
| 10. | Internet | - | RFQ | BBA | GOB | 6 | - | - | - | - | - | - | - | - | - | - |
| Total | 90 |

Admin. Wing

| Package No. | Description of procurement package goods | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (Lakh) | Time Code for process | Not Used in goods | Invite Advertise/ Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract Signing | Time for Completion of Contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
|  | Stationary, Electric, Computer Appliance and Consumable goods during the financial year 2017-2018 | enclosed | As per list | OTM | Executive Director | BBA | 18.00 | - | - | - | - | - | - | - | - |  | 12 Months |
|  | Recruitment |  | As per list |  | Executive Director | BBA | 20.00 | - | - |  |  | - | - | - | - |  | 12 Months |
|  | Furniture |  | As per list | RFQ/ OTM | Executive Director | BBA | 8.00 |  |  |  |  |  |  |  |  |  | 12 Months |
| Total | 46.00 |

Admin. Wing (estate section)

Goods

| Package No. | Description of procurement package goods | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (Lakh) | Time Code for process | Not Used in goods | Invite Advertise/ Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract Signing | Time for Completion of Contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 2 | Maintenance of BB Resort | 5 |  | RFQ | BBA | GOB | 14.00 |  |  | Sep/18 | Oct/18 | Oct/18 | Nov/18 | Nov/18 | Dec/18 | 8 Months | 8 Months |
| Total | 14.00 |

Works

| Package No. | Description of procurement package goods | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (Lakh) | Time Code for process | Not Used in goods | Invite Advertise/ Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract Signing | Time for Completion of Contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 2 | Repair of BB Resort | 1 |  | RFQ | BBA | GOB | 6.00 |  |  | June/18 | July/18 | July/18 | July/18 | July/18 | Aug/18 | 1 Months | 2 Months |
| Total | 6.00 |

Admin. Wing (Vehicle section)

| Package No. | Description of procurement package goods | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Funds | Estd. Cost in Tk. (Lakh) | Time Code for process | Not Used in goods | Invite Advertise/ Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract Signing | Time for Completion of Contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| 1. | Transport Fuel ( Octane/Diesal/CNG & Lubricants) | As per require ment | As per require ment | Direct purchase | As per authority delegated | BBA | 80.00 | Planned dates | July 2018 to June 2019 |
|  |  |  |  |  |  |  |  | Planned days |  |
| 2. | Maintenance & Repair of vehicle | As per require ment | As per require ment | DM/RFQ/LTM | As per authority delegated | BBA | 25.00 | Planned dates | July 2018 to June 2019 |
|  |  |  |  |  |  |  |  | Planned days |  |

Annual Procurement Plan (2018-2019)

| Ministry/ Division |  | Ministry of Road Transport & Bridges/Bridges Division |  |
| --- | --- | --- | --- |
| Agency |  | Bangladesh Bridge Authority |  |  |
| Procuring Entity Name & Code |  | Bangladesh Bridge Authority | 7105 |  |  |
| Project/ Program Name & Code |  | Finance & Accounts Wing |  |  |  |

| Pakage No. | Description of Procurement Item as per DPP SERVICES | Unit | Quantity | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost (In lakh Taka) | Time code for process | Invitation for EOI | Issue RFP | Technical proposal opening | Technical proposal Evaluation | Financial proposal opening & Evaluation | Negotiation | Approval | Signing of Contract | Total time for Contract signing | Time for completion of contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| SD1 | Appointment of Auditor for Auditing Revenue and Income collected from Bangubandhu Bridge and Mukterpur Bridge for FY 2018-19 & 2019-20. | Month | 6 | Direct/RFQ | Executive Director | BBA | 2.00 | Planned Dates | Sep/18 | - | - | - | Sep/18 | Oct/18 | Oct/18 | Nov/18 |  | 6 Months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  | 03 months |  |
| SD2 | Appointment of Income Tax Advisor for Nov-2017- Nov-2020 | Year | 3 | Direct | Executive Director | BBA | 3.00 | Planned Dates | Jul/18 | - | - | - | Jul/18 | Aug/18 | Aug/18 | Sep/18 |  | 3 Years |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  | 03 months |  |
| SD3 | ERP Software installation in site office | No. | 1 | Direct | Executive Director | BBA | 1.30 | Planned Dates | Aug/18 | - | - | - | Sep/18 | Oct/18 | Oct/18 | Nov/18 |  | 1 Years |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  | 03 months |  |

Annual Procurement Plan (2018-2019)

| Ministry/ Division |  | Ministry of Road Transport & Bridges/Bridges Division |  |
| --- | --- | --- | --- |
| Agency |  | Bangladesh Bridge Authority |  |  |
| Procuring Entity Name & Code |  | Bangladesh Bridge Authority | 7105 |  |  |
| Project/ Program Name & Code |  | Planning & Development Wing |  |  |  |

| Pakage No. | Description of Procurement Item as per DPP SERVICES | Unit | Quantity | Procurement Method & (Type) | Contract Approving Authority | Source of Funds | Estd. Cost (In lakh Taka) | Time code for process | Invitation for EOI | Issue RFP | Technical proposal opening | Technical proposal Evaluation | Financial proposal opening & Evaluation | Negotiation | Approval | Signing of Contract | Total time for Contract signing | Time for completion of contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |
| SD1 | Appointment of Consultant for Impact assessment of Bangubandhu Bridge | Month | 06 | DPM | Executive Director | BBA | 150.00 | Planned Dates | Sep/18 | - | - | - | Sep/18 | Oct/18 | Oct/18 | Nov/18 |  | 06 Months |
|  |  |  |  |  |  |  |  | Planned Days |  |  |  |  |  |  |  |  | 90 Days |  |